## Tabelle1
Risk Name | Risk Description | Risk Probability of Occurrence | Risk Impact (1-10) | Risk Factor | Risk Migration | Person in Charge of Tracking (not person who brought it up!!)
Personnel deficits | One or more teammembers fall out | 30% | 9 | 2.7 | Redestribute workload and responsibilities. | everybody
unrealistic deadlines | Missplanned deadlines or underestimation | 55% | 4 | 2.2 | Replan deadlines, cut workload | Mehmet Ali Incekara
Unrealistic use cases | Use cases are to big to get implemented | 70% | 3 | 2.1 | Split into smaller use cases or abort. | Mehmet Ali Incekara
loss of knowledge | Loss of Knowledge after a longer break | 75% | 2 | 1.5 | relearn and new planning | everybody
technical issues | Technical issues from one or more teammembers | 90% | 1 | 0.9 | Fix issues alone or with help from the others | everybody
0
0
0
0
0
0
0
0
0
0
0